## 291RT P700 PQP
Current Stage: | 5. Contract Admin & Inspect. |  | Note: When pasting in this document, please retain destination formatting (i.e. paste "as values") | [8 empty] | 1. Project Overview | 4. Planning & Design | 7. Additional Services
GENL-PQP-04-01-01 | Rev03 (April 2023) | [9 empty] | Comments or | 2. Project Team | 5. Documentation & Tender | 8. Close-Out & Feedback
HN Project Number: |  | 291RT P700 | Project Name: | The Upgrade of Main Road P700 | [6 empty] | Instructions | 3. Appointment & Milestones | 6. Works & Handover
1. PROJECT OVERVIEW | [10 empty] | Comments
Project Description: |  | The Upgrade of Main Road P700
Project Location: |  | Heatonville
Client Organisation: |  | KZN Department of Transport |  | VAT Number: | N/A
Primary Contact Name: |  | Malibongwe Buthelezi |  | Contact Person Designation: | Project Manager
Invoice Address: |  | 224 Prince Alfred Street, Pietermaritzburg, 3201.
2. PROJECT TEAM
Lead Consultant: |  | HN Consulting Engineers (Pty) Ltd |  |  |  | Subconsultant to HN? | Subconsultant Agreement | CPG Partner?
Professional Team: | [8 empty] | 0%
Role | Req'd | Organisation Responsible | Representative Name | Email | Cell |  |  |  | CPG % |  | Comments / Details
Employer's Proj. Man. | ✓ | KZN Department of Transport | Njabulo Vezi | njabulo.vezi@kzntransport.gov.za | 076 751 0411 | - | - | - | 0%
HN Project Director | ✓ | HN Consulting Engineers (Pty) Ltd | Ntembeko Zifuku | ntembeko@hn.co.za | 083 965 7383 | - | - | - | 0%
Civil Engineer | ✓ | HN Consulting Engineers (Pty) Ltd | Ntembeko Zifuku | ntembeko@hn.co.za | 083 965 7383 | - | - | - | 0%
Structural Engineer | ✓ | HN Consulting Engineers (Pty) Ltd | Ntembeko Zifuku | ntembeko@hn.co.za | 083 965 7383 | - | - | - | 0%
Enviro Approval | - |  |  |  |  | - | - | - | 0%
Enviro Control Officer | ✓ | Kusini Environmental Services | Poppy Dlamini | poppy@kusinienviro.co.za | 083 300 7053 | ✓ | ✓ | - | 0%
H&S Auditor | ✓ | Phungashe H&S Consulting | Ayanda Buthelezi | ayanda.phungashe@gmail.com | 061 416 2618 | ✓ | ✓ | - | 0% |  | Agreement signed 17 Mar 2020
Topo Surveyor | ✓ | Nqoba Konke Surveys, Mapping | Mfundo Ndlovu | nqobakonke@webmail.co.za | 067 838 3798 | ✓ | - | - | 0% |  | Agreement not signed by subconsultant
Training Provider | ✓ | Novi General Services | Sibisi Nonhlanhla | sylvinahh@gmail.com | - | - | - | - | 0% |  | Paid through the main contract
Geotech Survey | - |  |  |  |  | - | - | - | 0%
Soils Laboratory | ✓ | Geosure (Pty) Ltd | Dheeran Ramcharan | dheeran@geosure.co.za | 083 309 7916 | ✓ | ✓ | - | 0% |  | Agreement signed 17 Mar 2020
Traffic Count | - |  |  |  |  | - | - | - | 0%
Architect | - |  |  |  |  | - | - | - | 0%
Quantity Surveyor | - |  |  |  |  | - | - | - | 0%
Electrical Engineer | - |  |  |  |  | - | - | - | 0%
Mechanical Engineer | - |  |  |  |  | - | - | - | 0%
Civil Engineer (CPG) | - |  |  |  |  | - | - | - | 0%
Other (Specify) | - |  |  |  |  | - | - | - | 0%
Comments (if any):
3. HN APPOINTMENT & MILESTONES | [10 empty] | Comments
| In Place | Date | Filing Location | Notes
Brief from Client: | ✓ | 2020-02-14 | K:\02 RT\291RT - KZN DoT Capital\10 P700 Upgrade\00 Proj Man\01 Appointment | Confirmation of Interest
Appointment / SLA / Fees Order | ✓ | 2020-03-04 | K:\02 RT\291RT - KZN DoT Capital\10 P700 Upgrade\00 Proj Man\01 Appointment | Appointment letter signed by HoD | [6 empty] | P700 Fees Order E0192775 - 20200309 - R33 819 080.71
Director's Review | Name: | Ntembeko | Comments: | There are numerous existing crises on this project. However, we have the
of Appointment: | Date: | 2020-03-04 | expertise to resolve the challenges.
The information lacking in the appointment letter I have clarified in our "Confirmation of Interest"
letter that preceded it. We are struggling to get comprehensive information from previous consultants
via the client. However, we can proceed and make the best of the information provided.
HN's Roles: | Civil and Structural Engineer
For more detail, refer to Client's brief.
HN Scope & Deliverables: | Applicable to HN | ECSA Project Stage | Date Completed | Notes / Description of Deliverable |  |  | Deliverable Required | Deliverable Submitted | Employer Approved | Incomplete | Comments
| - | 1. Inception |  | Done by previous consultants | [5 empty] | -
| - | 2. Concept & Viability |  | Done by previous consultants | [5 empty] | -
| - | 3. Design Development |  | Done by previous consultants | [5 empty] | -
| ✓ | 4. Doc. & Procurement | 2022-12-15 | Tender Doc: ZNB921 (P700 km68,92 to km75,0) |  |  | ✓ | ✓ | ✓ | -
| ✓ | 5. Contract Admin & Inspect. |  | Deliverables: Final Approval Cert & Handover to Region |  |  | ✓ |  |  | ✓
| ✓ | 6. Close-Out |  | Close Out Report |  |  | ✓ |  |  | ✓
| - | 7. Additional Services |  | - | [5 empty] | -
Appointment Date: |  | 2020-03-04 | Expected Duration: | 4 years | Contract / Ref No: | ZNT2598/1/15T
Original End Date: |  | Not specified
Comments: | km 36-68: Ancillary works required - tender doc. drafted. |  |  | km68-75: ZNB921 finishing contract. Awaiting award.
(if any) | km75-80: Construction underway (Xmoor) |  |  | km80-km84,5: Construction underway (ESOR-James)
4. PLANNING AND DESIGN (ECSA Stage 1-3) | [10 empty] | Comments
Design Criteria / | Designs completed by previous consultants (iBhongo, RHDHV) | [9 empty] | Refer to design report, if sufficient, rather than duplicating here.
Requirements: | Limited technical information provided, apart from tender docs for km75-km80 and km80-km84,5.
Planning & Design Risks: |  | GENL-RSK-04-01-03 (General Planning & Design Risks)
Project-specific | Risk or Challenge (Planning/Design-related) |  |  | Mitigating Measures Required |  | Record of Action Taken |  |  |  |  | List risks in addition to GENL-RSK-04-01-03, or say "nil".
Risks (if any): | Refer to monthly and status quo reports
Pre-Construction Authorisations: | Required | Approval Type | Date Approved | Status / Reference No. |  |  | Deliverable Required | Deliverable Submitted | Approved
| - | Enviro Approval | 2005-10-28 | Record of Decision: EIA/4635 |  | K:\02 RT\291RT - KZN DoT Capital\10 P700 Upgrade\00 Proj Man\02 Specialist Services\04 Enviro\03 Enviro Documentation | - | - | ✓
| - | WULA | 2018-04-23 | General Authorisation (23 Apr 2018) |  | K:\02 RT\291RT - KZN DoT Capital\10 P700 Upgrade\ZNT3568-14T Esor-James\05 Works\23 Enviro\01 Authorisations | - | - | ✓
| - | Construction Work Permit |  | CWP will be required for ZNB921 km68-km75 |  |  | ✓ | - | -
| - | [5 empty] | - | - | -
| - | [5 empty] | - | - | -
| - | [5 empty] | - | - | -
| - | [5 empty] | - | - | -
| - | [5 empty] | - | - | -
Scope Register: | Blank Template: GENL-SCO-04-01-01
Location of Project Scope Register:
Design Notes: | Designs completed by previous consultants (iBhongo, RHDHV) | [9 empty] | Refer to minutes or existing reports, if necessary, rather than duplicating info.
Design of bridge decks for Heatonville and Ngogodo (km75-km80) had insufficient steel. Revised by previous consultants. Decks being rebuilt.
- HN checked revised designs and increased capacity of bridge bearings
5. DOCUMENTATION AND PROCUREMENT (ECSA Stage 4)
Client Tender Doc | ZNT3568/14T and ZNT3441/13T done by previous consultant (GCC 2015 and COLTO 1998) |  |  |  | Form of Contract: |  | GCC 2015
Requirements: | ZNB921: Done by HN (GCC 2015 and COTO 2020). Client template: 01 08 2022. |  |  |  | Standard Specs: |  | COTO 2020
(eg. Doc Template) |  |  |  |  | Client Template?: |  | 01/08/2022 COTO
Documentation Risks: |  | GENL-RSK-04-01-04 (General Documentation & Procurement Risks)
Project-specific | Risk or Challenge (Documentation Phase) |  |  | Mitigating Measures Required |  | Record of Action Taken |  |  |  |  | List risks in addition to GENL-RSK-04-01-04, or say "nil".
Risks (if any): | Lengthy duration awaiting for award of ZNB921. |  |  | Followed up verbally with client in Sep 2023. |  | -
Tender Phase | ZNT3568/14T and ZNT3441/13T done by previous consultant (GCC 2015 and COLTO 1998)
Notes: | ZNB921: Document prepared by by HN (GCC 2015 and COTO 2020) using client template: 01 08 2022. Tenders closed 15 Feb 2023.
Awaiting award of ZNB 00921/00000/00/HOD/INF/21/T.
6. WORKS AND HANDOVER (ECSA Stage 5)
Construction Contract Details:
Contract Description |  | The Construction of Earthworks, Layerworks, Surfacing and Road Furniture on Main Road P700, km80,0 to km84,50 | [8 empty] | Comments
Contractor Organisation: |  | ESOR/James Joint Venture |  | Contract Number: | ZNT3568/14T
Award Value (incl. VAT): |  | 99565789.48 | Milestones: | Commencement Date: | 2019-06-18 | Original Duration:
Award Date: |  | 2019-02-15 |  | Due Completion Date (Orig): | 2020-09-18
Original Order No: |  | E0064940 |  | Due Completion Date (Latest): | 2023-05-01
Original Order Date: |  | 2019-02-15 |  | Practical Completion: |  |  | (✓ = Signed by Employer)
Inception Meeting Date: |  | 2019-06-13 |  | Completion: |  |  | (✓ = Signed by Employer)
Final Payment Cert Date: |  |  |  | Final Approval: |  |  | (✓ = Signed by Employer)
Final Value (incl VAT): |  |  |  | Client Takeover Date: |  |  | (✓ = Signed by Employer)
Commencement of |  | Requirements for commencement as per Contract Data, Inception Meeting & Progress Meeting Minutes
Works: |  | Date of EA's Instruction: | (Prior to HN) | Where instruction is recorded: | (Prior to HN) | [5 empty] | e.g. email stored on server
Appointments: | Role |  | Date Appointed | Name | Record of Appointment | [5 empty] | Comments
| Employer's Agent |  | 2020-08-01 | Dion Govinder | Email |  |  |  | K:\02 RT\291RT - KZN DoT Capital\10 P700 Upgrade\ZNT3568-14T Esor-James\05 Works\03 Appointments\Engineer
| Employer's Agent's Representative |  | 2020-11-01 | Zomkhozi Mdladla | Duties of EAR |  |  |  | K:\02 RT\291RT - KZN DoT Capital\10 P700 Upgrade\ZNT3568-14T Esor-James\05 Works\03 Appointments\EAR |  | Previous EAR: Mary Mpila (passed away)
| Construction Manager (Site Agent) |  | (Pre-HN) | David Dickerson | Appointed prior to HN taking over
Other: See Inception / Progress Meeting Minutes
Responsibilities: | GENL-WIN-04-07-01: Project Director
Link to these docs | GENL-WIN-04-07-02: Employer's Agent
GENL-WIN-04-07-03: Employer's Agent's Representative
Construction Phase Risks: |  | GENL-RSK-04-01-05 (General Construction Phase Risks)
Project-specific | Risk or Challenge (Construction Phase) |  |  | Mitigating Measures Required |  | Record of Action Taken |  |  |  |  | List risks in addition to GENL-RSK-04-01-05, or say "nil". For challenges, refer to Status Quo reports.
Risks (if any): | Works were suspended on 28 Jun 2023 while awaiting additional funds (VO 12). This was first requested in Sep 2022. |  |  | VO for additional funds first submitted Sep 2022. |  | K:\02 RT\291RT - KZN DoT Capital\10 P700 Upgrade\ZNT3568-14T Esor-James\05 Works\22 Financial\06 VO's\VO 12 - Additional Funding - CPA & Time |  |  |  |  | The time-frames for BAC approval are becoming long and impractical. However, this is a delay outside our control.
| Suspension is due to expire 05 Oct 2023. |  |  | 04 Oct 2023: PQ emailed Khumbu requesting extension of suspension. |  | K:\02 RT\291RT - KZN DoT Capital\10 P700 Upgrade\ZNT3568-14T Esor-James\05 Works\22 Financial\Suspension June 2023
Construction | [10 empty] | Refer to minutes or existing reports, if necessary, rather than duplicating info.
Phase Notes:
For more information, see Status Quo reports:
K:\02 RT\291RT - KZN DoT Capital\10 P700 Upgrade\00 Proj Man\08 Reporting\03 Status Quo
7. ADDITIONAL/OTHER SERVICES (if any) | [10 empty] | Comments
List Additional | Nil | [9 empty] | Refer to minutes or existing reports, if necessary, rather than duplicating info.
work done
outside ECSA 1-6:
Project-specific | Risk or Challenge (Additional Services) |  |  | Mitigating Measures Required |  | Record of Action Taken |  |  |  |  | Indicate risks/challenges or say "nil"
Risks (if any): | N/A
Notes: | Nil | [9 empty] | Refer to minutes or existing reports, if necessary, rather than duplicating info.
8. CLOSE-OUT & FEEDBACK | [10 empty] | Comments
Date CSQ Submitted: |  | 2021-11-12 | Date CSQ Received: | 2021-11-12 | CSQ Rating: | 82.22% |  | Location: | K:\02 RT\291RT - KZN DoT Capital\10 P700 Upgrade\00 Proj Man\11 CSQ
Comments on Feedback: |  | Generally encouraging feedback.
The lowest marks we got were "3: Satisfactory": Construction administration, promptness in responding to queries, innovation,
drawings and value-for-money. We invited the Employer to provide more details and he did not respond.
Actual Close-Out Date: |  | (Blank)
General Remarks / |  | The BAC is taking sometimes over a year to approve variation orders. This makes managing the contract very difficult.
Lessons Learned: |  | It is so important to provide enough allowance in the original contract for
Note on B20: Which consultant is the "Lead Consultant" or "Principal Agent", being the primary link with the client?
Note on K23: Target share of the work if CPG partner
Note on B25: Director reponsible for fee accounts, setting up PQP and allocating resources.
Note on B57: e.g. Civil Engineer, Structural Engineer, etc.

## PQP Tables
| Project ID | #NAME?
|  | 4 | 4 | 4 | 4 | 7 | 7 | 4
|  | 9 | 11 | 13 | 14 | 13 | 14 | 16
Section 1 — PROJECT OVERVIEW
| id | Project Description | Location | Client Organisation | Primary Contact Name | VAT Number | Designation | Invoice Address
9 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
|  | 4 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 13
|  | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24
Section 2
| id | Role | Req'd | Organisation | Representative Name | Email | Cell | Subconsultant to HN? | Subconsultant Agreement? | CPG Partner? | CPG % | Comments
24 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
25 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
26 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
27 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
28 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
29 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
30 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
31 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
32 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
33 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
34 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
35 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
36 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
37 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
38 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
39 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
40 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
41 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
|  | 3 | 4 | 5 | 6 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 4 | 6 | 8 | 3
|  | 48 | 48 | 48 | 48 | 57 | 61 | 61 | 61 | 61 | 61 | 61 | 69 | 69 | 69 | 72
Section 3
| id | In Place | Date | Filing Location | Notes | HN Roles | ECSA Project Stage | Date Completed | Description of Deliverable | Deliverable? | Deliverable Accepted? | Employer Approved? | Appointment Date | Expected Duration | Contract/Ref No | Comments
| #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
[7 empty] | 4 | 5 | 6 | 7 | 8 | 9
| id | In Place | Date | Filing Location | Notes | HN Roles | ECSA Project Stage | Date Completed | Description of Deliverable | Deliverable? | Deliverable Accepted? | Employer Approved? | Appointment Date | Expected Duration | Contract/Ref No | Comments
61 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
62 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
63 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
64 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
65 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
66 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
Section 4
| id | Design Criteria/Requirements | Planning & Design Risks | Projectâ€‘specific Risks | Mitigating Measures | Record of Action Taken | Approval Type | Date Approved | Status/Reference No. | Deliverable? | Deliverable Accepted? | Approved? | Scope Register Location | Design Notes
| #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
Section 5
| id | Client Tender Doc Requirements | Form of Contract | Standard Specs | Client Template Date | Documentation Risks | Projectâ€‘specific Risks | Mitigating Measures | Record of Action Taken | Tender Phase Notes
| #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
Section 6
| id | Construction Description | Contractor Organisation | Contract Number | Award Value (incl. VAT) | Award Date | Original Order No. | Original Date Order | Inception Meeting Date | Final Payment Cert Date | Final Value (incl VAT) | Milestones | Commencement of Works | Date of EA's Instruction | Where Instruction is recorded | Employer's Agent | Employer's Agent Representative | Construction Manager (Site Agent) | Record of Appointment Links | Responsibilities Links | Construction Phase Risks | Projectâ€‘specific Risks | Mitigating Measures | Record of Action Taken | Construction Phase Notes
| #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
Section 7
| id | 4: Additional Services Done; 3: Projectâ€‘specific Risks; 4: Mitigating Measures; 5: Record of Action Taken; 6: Notes
| #NAME? | 4: #NAME?; 3: #NAME?; 4: #NAME?; 5: #NAME?; 6: #NAME?
Section 8
| id | Date CSQ Submitted | Date CSQ Received | CSQ Rating | Location | Comments on Feedback | Actual Closeâ€‘Out Date | General Remarks/Lessons Learned
| #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
1
Section 9
| id | 4: Scope Item; 3: Category; 4: Owner; 5: Status; 6: Due Date; 7: Notes
| #NAME? | 4: #NAME?; 3: #NAME?; 4: #NAME?; 5: #NAME?; 6: #NAME?; 7: #NAME?
Section 10
#NAME?